SOFTWARE PROJECT PLAN

Wildlife Information System

(WIS)

Document Number: WIS-PP-001

Version: 2.0

Date: September 2026

Prepared by

Muhammad Abbas

Muhammad Ehtisham

Fahad Naeem Khan

# Front Matter

## Document Control

| Document title | Software Project Plan — Wildlife Information System (WIS) |
| --- | --- |
| Document number | WIS-PP-001 |
| Version | 2.0 |
| Date | September 2026 |
| Status | Draft for team and supervisor review |
| Prepared by | Muhammad Abbas, Muhammad Ehtisham, Fahad Naeem Khan |
| Source document | Wildlife Information System SRS, Version 2.0, June 2026 (WIS-SRS-001) |

## Revision History

| Version | Date | Description |
| --- | --- | --- |
| 1.0 | June 2026 | Initial requirements captured in the SRS (WIS-SRS-001). |
| 2.0 | September 2026 | Project Plan prepared from SRS Version 2.0, organised into overview, references, definitions, context, planning, supporting process plans and risk management. |

## Purpose of This Document

This Project Plan describes how the Wildlife Information System will be planned and  organized, built, tested and delivered. It reorganizes the requirements, scope, technology choices, schedule and test strategy defined in the WIS SRS Version 2.0 into a project-management view. The risk-management section is a planning addition derived from the assumptions, dependencies, scope and architecture in the SRS; it should be reviewed and updated by the team during development.

## Contents

1. Project Overview

2. References

3. Definitions

4. Project Context

5. Project Planning

6. Supporting Process Plans

7. Risk Management

8. Key System Interface and API Requirements

9. Implementation Status

10. Traceability to the Plan Outline

# 1. Project Overview

## 1.1 Project Summary

The Wildlife Information System (WIS) is a centralized system for storing and sharing wildlife information in one organized database. In Pakistan and many other countries, wildlife data is scattered across government departments, universities, conservation organizations, spreadsheets, reports, notebooks, paper records and private GPS/IoT systems. WIS brings this data together and makes it available to authorized users.

The system covers animal profiles, population information, movement records, DNA and biological data, health and veterinary records, and behavior and environment data. It provides a RESTful API with JSON responses for authorized access and a basic web interface for searching and manual data entry.

## 1.2 Purpose, Scope and Objectives

Purpose: Reduce wildlife-data fragmentation and provide a central repository that supports research, wildlife monitoring, conservation projects and decision making.

Scope: A central PostgreSQL database; a backend that validates, organizes and manages incoming data (field researchers, IoT tracking devices, lab results); a RESTful API; role-based access for Data Entry Operators, Researchers, Government Officials, System Administrators and API developers; and a basic web interface for search and manual data entry.

Primary objective: Build a centralized wildlife information database that is accurate, well organized and accessible through an API for research and analysis.

Secondary objectives:

- Encourage data sharing among wildlife organizations.

- Provide a platform that supports conservation and research decision making.

- Build a scalable foundation that can grow with more data and users over time.

## 1.3 Assumptions and Constraints

- Users of the web portal and API have constant network connectivity.

- WIS acts strictly as a storage repository for GPS data generated by external tracking hardware; it does not manufacture or install tracking devices.

- Version 1.0 operates in English only.

- External applications access WIS programmatically through the RESTful API using JWT tokens.

- The project is delivered by a three-member team on a fixed ten-week schedule.

## 1.4 Project Deliverables

| # | Deliverable | Phase |
| --- | --- | --- |
| D1 | Requirements and SRS documentation | Phase 1 |
| D2 | PostgreSQL database design / schema (ER diagram) | Phase 2 |
| D3 | RESTful API design and endpoint specification | Phase 2 |
| D4 | Authentication and role-management design (JWT, bcrypt) | Phase 2 |
| D5 | Basic HTML/CSS/JavaScript web interface design | Phase 2 |
| D6 | Node.js/Express backend and database setup | Phase 3 |
| D7 | Working RESTful API with test results | Phase 4 |
| D8 | Testing plan and test cases | Phases 4–5 |
| D9 | Final project documentation and review | Phase 5 |

## 1.5 Schedule Summary

| Phase | Activity | Duration |
| --- | --- | --- |
| Phase 1 | Requirements gathering and analysis | 2 weeks |
| Phase 2 | System design (DB schema, API design) | 2 weeks |
| Phase 3 | Backend development and database setup | 3 weeks |
| Phase 4 | API development and testing | 2 weeks |
| Phase 5 | Documentation and final review | 1 week |
| Total |  | 10 weeks |

## 1.6 User Roles

| Role | Access | Capabilities |
| --- | --- | --- |
| Admin | Full | Supervise user accounts, perform CRUD on all entities, and modify configurations. |
| Data Entry Operator | Write + Read | Create or modify wildlife profiles, including tracking, medical and genetic data. |
| Researcher | Read + Export | Query data through the portal/API and download records in CSV or JSON. |
| Government Official | Read Only | View and search existing animal information and profiles. |
| Developer / API Client | API Read | Retrieve data from authenticated public API endpoints using JWT tokens. |

# 2. References

- Wildlife Information System SRS, Version 2.0, June 2026 (WIS-SRS-001).

- Pressman, R. S., Software Engineering: A Practitioner's Approach.

- Mohapatra, P. K. J., Software Engineering: A Lifecycle Approach.

# 3. Definitions

| Term | Definition |
| --- | --- |
| WIS | Wildlife Information System |
| API | Application Programming Interface |
| REST | Representational State Transfer |
| JWT | JSON Web Token |
| FR | Functional Requirement |
| NFR | Non-Functional Requirement |
| UC | Use Case |
| CRUD | Create, Read, Update, Delete |
| CSV | Comma-Separated Values |
| JSON | JavaScript Object Notation |
| DFD | Data Flow Diagram |
| ER | Entity-Relationship |
| SRS | Software Requirements Specification |

# 4. Project Context

## 4.1 Existing System and Problem

| Area | Description |
| --- | --- |
| Existing system | Government forest departments keep paper or spreadsheet records; universities store field data in local, non-public databases; international bodies (WWF, IUCN) maintain global databases that lack local detail; GPS-collar data is kept private. |
| Main issues | Data isolation, no standard format, lack of open access, missed analytical opportunities (e.g. disease outbreaks, migration changes, population decline) and duplicated research effort. |
| Problem statement | No single system in Pakistan stores and shares wildlife information, so researchers duplicate data collection and agencies may decide without complete data. |
| Proposed solution | A centralized wildlife database with controlled web access and a secure RESTful API. |
| Primary entities | Animal (central), Species, Movement Record, DNA Sample, Health Record, User and Location. One Animal has many Movement, Health and DNA records; each Animal belongs to one Species. |

## 4.2 Technological Overview

| Component | Technology |
| --- | --- |
| Backend | Node.js with Express.js |
| Database | PostgreSQL 14+ (relational, structured data) |
| API | RESTful API with JSON responses |
| Authentication | JWT (JSON Web Tokens); passwords hashed with bcrypt and salt |
| Frontend | HTML, CSS, JavaScript (basic web interface) |
| Version control | Git / GitHub |
| API testing | Postman |
| Editor / browsers | VS Code; Chrome / Firefox |
| Hosting (future) | Cloud (AWS or DigitalOcean) |
| Data formats | JSON; CSV for exports and bulk upload |

## 4.3 System Architecture

WIS follows a 3-tier architecture. External users and applications communicate with the application layer through the RESTful API.

| Layer | Component | Responsibility |
| --- | --- | --- |
| Presentation | HTML/CSS/JS web interface | Basic UI for data entry, search and export |
| Application | Node.js + Express.js API server | Business logic, authentication, query processing |
| Data | PostgreSQL database | Stores wildlife records, users and audit logs |

## 4.4 Functional Requirements

| ID | Requirement | Description |
| --- | --- | --- |
| FR-01 | Animal Profile Management | Add, update and remove animal records; system-generated unique IDs; validation of submitted data (species, age, weight, etc.). |
| FR-02 | Movement Data Recording | Store GPS coordinates and timestamps linked to animal IDs; CSV batch upload; coordinate validation before saving. |
| FR-03 | DNA & Biological Data | Store DNA samples, lab results and species confirmation, linked to an animal profile. |
| FR-04 | Health & Veterinary Records | Record vaccinations, diagnosed conditions and treatments, with date of service and a brief summary. |
| FR-05 | RESTful API Access | Authenticated JSON endpoints for resources such as animals, movements and species; token required on every request. |
| FR-06 | User Management | Admins create/update/deactivate users and assign roles; bcrypt password hashing; unique, verified email. |
| FR-07 | Search & Filter | Search by species, location and time frame with paginated results. |
| FR-08 | CSV Bulk Upload | Validate every row, save valid rows and report skipped rows with reasons. |
| FR-09 | Data Export | Export search results as CSV or JSON via web interface and API. |

## 4.5 Non-Functional Requirements

| ID | Type | Requirement |
| --- | --- | --- |
| NFR-01 | Performance | Standard API queries return within 2 seconds. |
| NFR-02 | Scalability | Database handles up to 1 million animal records without performance loss. |
| NFR-03 | Security | All API calls require JWT; passwords hashed with bcrypt and salted. |
| NFR-04 | Availability | 99% availability after deployment. |
| NFR-05 | Data Integrity | All records carry timestamps and audit logs showing who created or modified them. |
| NFR-06 | Usability | Simple web interface usable by non-technical data entry operators without training. |
| NFR-07 | Compatibility | REST API works with any language or tool able to consume REST/JSON. |

## 4.6 Use-Case Summary

| ID | Use Case | Actor | Purpose |
| --- | --- | --- | --- |
| UC-01 | Add Animal Record | Data Entry Operator | Enter validated animal details and save a record with a unique ID. |
| UC-02 | Query Animal Data via API | Researcher / External App | Retrieve matching animal records as JSON using a valid JWT. |
| UC-03 | Upload CSV Movement Data | Data Entry Operator | Upload and validate movement data (animal_id, lat, lng, timestamp). |
| UC-04 | Search Animals | Researcher / Gov. Official | Search by species/location with optional date range (20 per page). |
| UC-05 | Manage Users | System Administrator | Create users and update roles/status. |
| UC-06 | View Health Records | Researcher / Veterinarian | Retrieve health records for a selected animal. |
| UC-07 | Export Data | Researcher | Export filtered records as CSV or JSON. |
| UC-08 | User Login / Authentication | All Users | Authenticate and receive a JWT token. |
| UC-09 | Add DNA Sample Record | Data Entry Operator | Create a DNA record linked to an existing animal. |

## 4.7 Scope Exclusions

- No installation, manufacturing or design of GPS collars or tracking devices.

- No real-time live tracking maps or animated movement visualization (possible future extension).

- No Android/iOS mobile application; third parties may build one on the public API.

- No AI/ML-based animal identification or pattern recognition.

- No direct integration with international databases (e.g. IUCN Red List, CITES) in v1.0.

- No financial, HR, payroll or administrative management features.

- No offline field data-collection tools.

- No automatic alerts for disease outbreaks, environmental risks or illegal hunting.

- No multilingual support in v1.0 (English only).

- No wildlife permit, legal reporting or enforcement tracking.

# 5. Project Planning

## 5.1 Development Process Model

The project follows an Incremental Development Model: the system is built step by step, with each increment adding functionality and improving the previous one. This model was chosen because requirements are mostly clear but small changes are expected, it allows early testing of the database and API before the full system exists, and each increment produces a working version that can be reviewed.

| Increment | Planned functionality | Indicative phases |
| --- | --- | --- |
| Increment 1 | Database design and basic data-entry system. | Phases 2–3 |
| Increment 2 | API development and user authentication. | Phases 3–4 |
| Increment 3 | Search, filtering, export and final testing. | Phases 4–5 |

## 5.2 Project Schedule

| Phase | Activity | Duration | Weeks |
| --- | --- | --- | --- |
| Phase 1 | Requirements gathering and analysis | 2 weeks | 1–2 |
| Phase 2 | System design (DB schema, API design) | 2 weeks | 3–4 |
| Phase 3 | Backend development and database setup | 3 weeks | 5–7 |
| Phase 4 | API development and testing | 2 weeks | 8–9 |
| Phase 5 | Documentation and final review | 1 week | 10 |

Timeline overview (shaded cells show the weeks in which each phase is active):

## 5.3 Work Activities

| Phase | Work activities |
| --- | --- |
| Phase 1 | Collect and analyze requirements; define scope, user roles, use cases and the SRS. |
| Phase 2 | Design the PostgreSQL schema and ER diagram; design REST endpoints, JWT authentication and the web interface pages. |
| Phase 3 | Set up PostgreSQL; build the Node.js/Express backend, data-entry features (animals, DNA, health) and role-based access. |
| Phase 4 | Build and test API endpoints (movements, CSV upload, search, export); run unit and integration tests in Postman. |
| Phase 5 | Run system and acceptance tests; finalize documentation; conduct final review before submission. |

## 5.4 Milestones

| ID | Milestone | Target |
| --- | --- | --- |
| M1 | Requirements baselined (SRS complete) | End of week 2 |
| M2 | Database schema, API and interface design complete | End of week 4 |
| M3 | Backend and database operational; basic data entry working | End of week 7 |
| M4 | API complete and unit/integration tested | End of week 9 |
| M5 | System and acceptance testing passed; final documentation submitted | End of week 10 |

## 5.5 Resource Allocation

The SRS defines the technology stack and minimum hardware. Technical resources are:

| Resource | Specification / purpose |
| --- | --- |
| Development machine | Intel Core i3 (or equivalent) 2.0 GHz; 4 GB RAM minimum (8 GB recommended for development). |
| Database storage | At least 50 GB free disk space for the database. |
| Deployment server | 2 CPU cores, 4 GB RAM, 100 GB SSD cloud instance. |
| Network | Stable internet connection for portal and API access. |
| Software | Windows 10 / Ubuntu 20.04, Node.js v18+, PostgreSQL 14+, Postman, VS Code, Git, Chrome/Firefox. |

## 5.6 Team and Responsibilities

| Team member | Role |
| --- | --- |
| Muhammad Abbas | Project team member |
| Muhammad Ehtisham | Project team member and Leader |
| Fahad Naeem Khan | Project team member |

Work is shared across the team. Each member is assigned specific issues/tasks on the GitHub repository through GitHub Projects, so progress and ownership are visible and every task is completed on time.

## 5.7 Project Management and Communication

- GitHub Projects: task board with three columns — To Do (tasks not started), In Progress (tasks being worked on) and Done (completed tasks).

- Git / GitHub: version control and issue tracking.

- WhatsApp and Discord: day-to-day team communication.

- Google Docs: shared documentation.

- Weekly meetings: every Saturday to review progress against the schedule.

# 6. Supporting Process Plans

## 6.1 Quality / Validation Plan

Data quality is supported through mandatory fields, validation at submission, row-by-row CSV validation, coordinate integrity checks, unique identifiers, and timestamps with audit logs recording who created or modified each record. The API returns standard HTTP status codes (for example 400, 401, 403, 404, 409) so clients can handle errors consistently.

## 6.2 Testing Plan

Black Box Testing is the main approach. Tests are designed from input values and expected outputs only, which suits the API endpoints, validates functional requirements without reading code, and reflects how real users and external applications will use WIS.

| Test level | Approach | When |
| --- | --- | --- |
| Unit testing | Test each API endpoint individually using Postman. | After each endpoint, during development |
| Integration testing | Test all API endpoints together. | After the full API build (after Increment 2) |
| System testing | Test the complete flow from login through data export. | Final week |
| Acceptance testing | Verify the final system against the requirements. | Before submission |

Test tools: Postman for manual API testing and browser DevTools for the web interface.

## 6.3 Test Cases

| ID | Feature | Input | Expected output |
| --- | --- | --- | --- |
| TC-01 | User login | Valid email and password | JWT token returned, status 200 |
| TC-02 | User login (wrong) | Valid email, wrong password | Status 401 Unauthorized |
| TC-03 | Add animal | Valid animal data fields | Record saved, new ID returned |
| TC-04 | Add animal (missing) | Species name missing | Status 400, field error message |
| TC-05 | Get animal by ID | Valid animal ID in URL | Full animal record in JSON |
| TC-06 | Get animal (wrong ID) | ID that does not exist | Status 404 Not Found |
| TC-07 | Search by species | species=Snow Leopard | List of matching animals |
| TC-08 | CSV upload (valid) | Correctly formatted CSV | All rows saved successfully |
| TC-09 | CSV upload (bad) | CSV with missing coordinates | Rows skipped, error report shown |
| TC-10 | API without token | GET request without Auth header | Status 401 Unauthorized |
| TC-11 | Export data | Export search results | JSON or CSV file downloaded |
| TC-12 | Admin creates user | New user details with role | User account created successfully |

## 6.4 Configuration / Version Control Plan

All source code, database scripts and documentation are kept in a shared Git/GitHub repository. Work is tracked as GitHub issues on the GitHub Projects board (To Do, In Progress, Done), and each member works on assigned issues. Shared documents are maintained in Google Docs, and the team reviews changes in the weekly Saturday meeting.

## 6.5 Acceptance Criteria

- Users can log in and receive an access token.

- An authorized user can add an animal and retrieve it through the API.

- Movement CSV data can be uploaded and saved when valid.

- Search filters return the appropriate animals by species or geographic location.

- The API returns appropriate HTTP errors (401, 400, 404).

- An administrator can create a user and assign a role.

# 7. Risk Management

The risk register below is a planning addition derived from the risks implied by the SRS. The team should review it at the weekly meeting and update it as development progresses.

| ID | Risk | Potential impact | Priority | Mitigation / response |
| --- | --- | --- | --- | --- |
| R1 | Network dependency | Users cannot reliably access the portal or API. | High | Require stable network; return clear errors and standard HTTP responses. |
| R2 | Data quality | Invalid or inconsistent wildlife data enters the database. | High | Mandatory fields, validation, CSV row checks, unique IDs and audit logs. |
| R3 | Unauthorized access | Sensitive wildlife data exposed to an improper user. | High | JWT authentication, role-based access, bcrypt hashing, authorization checks on every endpoint. |
| R4 | Large data volume | Queries slow down as records grow toward 1 million. | Medium | Database indexing, query optimization, pagination; test with large data sets. |
| R5 | External tracking dependency | GPS data quality or availability depends on external devices. | Medium | Treat WIS as a repository only; validate incoming coordinates. |
| R6 | Scope expansion | Real-time maps, mobile apps, AI/ML or international integrations delay delivery. | Medium | Keep excluded features out of v1.0; log them as future phases. |
| R7 | Schedule slippage | Ten-week schedule is short for a three-member team. | Medium | Track progress weekly on GitHub Projects; deliver by increment so a working version exists early. |

## Risk Monitoring

Risks are reviewed in the weekly Saturday meeting. If a risk occurs, the team records it on the GitHub board, assigns an owner and applies the mitigation. Priority levels (High, Medium, Low) reflect combined likelihood and impact and may be revised as the project progresses.

# 8. Key System Interface and API Requirements

| Method | Endpoint | Purpose |
| --- | --- | --- |
| GET | /api/animals | Get animals with filters. |
| GET | /api/animals/:id | Get a single animal by ID. |
| POST | /api/animals | Add an animal record. |
| PUT | /api/animals/:id | Update an animal record. |
| DELETE | /api/animals/:id | Delete an animal record. |
| GET | /api/animals/:id/movements | Get movement history for an animal. |
| POST | /api/movements/upload | Bulk upload CSV movement data. |
| GET | /api/animals/:id/health | Get health records for an animal. |
| GET | /api/animals/:id/dna | Get DNA records for an animal. |
| POST | /api/auth/login | Authenticate a user and return a JWT. |
| GET | /api/species | Get the list of all species. |

## Web Interface Pages

Login page, dashboard, animal list, add-animal form, movement records page (with CSV upload), API documentation page and admin-only user management. The interface uses a minimal blue-and-white design; errors are shown in red and success messages in green.

# 9. Implementation Status

According to the SRS, the implementation stage had not yet begun. The system design, database model and API structure have been designed, and coding is planned as future work following the designs in the SRS (Section 4) and the schedule in this plan.

# 10. Traceability to the Plan Outline

| Plan outline item | Where addressed in this Project Plan |
| --- | --- |
| Front matter | Cover page, Document Control, Revision History |
| Project overview | Section 1 |
| References | Section 2 |
| Definitions | Section 3 |
| Project context | Section 4 |
| Project planning | Section 5 |
| Supporting process plans | Section 6 |
| Risk management | Section 7 |